## Sheet1
UAT Issue | Steps to reproduce | Requirement (Y/N) | QA Comments | Status After Internal Discussion
Releases – module functionality | Can ‘Release’ sub-module be renamed to ‘Releases’ | N | New Requirement
| Can ‘PROBE RELEASE’ be reflected as ‘PROBE Data Release’ | N | New Requirement
| Can ‘Data Release’ be reflected as ‘Other Data Release’ | N | New Requirement
| All clients ‘onekey’ data release has the below symbol – incorrect all clients are inactive | Y | As per the security file One Key is diabled for admin & GTM
| Allocate button has the above symbol when nothing is selected – incorrect, the ‘Allocate’ button should be greyed out until a client is selected or number under MFR/pack exception is selected | N | it is diabled , however kim wants the symbol to be removed
| I believe we need to add a ‘save’ button which only becomes active when ‘capital chemist’, ‘census’ or ‘onekey’ selection is amended | N | New Requirement
| Changing yes/no options – not own client | N | Kim wants the flag to be restricted to the client selection made and other line items flag should not allow to be changed
| Changing Astrazeneca ‘onekey’ from yes to no Didn’t allow user to change – correct, however this inactive for all clients including own - incorrect | N | As per the security file One Key is diabled for admin & GTM
| Changing yes/no options – own client Changing Glaxosmithkline from yes to no for capital chemist Allowed user to change – correct, didn’t save changes, incorrect | N | Needs SAVE button
Client name search | Why aren’t we leveraging the same methodology as pack search where it is a drop down list and clear search of x can be done? | N | New Requirement
PROBE Mfr search | Why aren’t we leveraging the same methodology as pack search where it is a drop down list and clear search of x can be done? | N | New Requirement
| Allocate mfr - not own client Allocate button becomes active - incorrect |  | Not Clear
Select mfr to remove – not own client | Remove button becomes active - incorrect Allows removal – incorrect |  | Not Clear
| Bring the third window into alignment with rest | N
Select mfr to remove – not own client | Remove button becomes active - incorrect Allows removal – incorrect | N | Not Clear
Select packs to add – own client | Middle screen doesn’t change to pack list - incorrect | Y | As per the security file it is diabled for admin & GTM
| For packs already selected can’t change product level – incorrect | N | As per the requirement the flag control is set at the pack exception seacrh screen
Select packs to remove – own client | Middle screen doesn’t change to pack list - incorrect |  | As per the security file it is active for production & support users ( not for admin)
| For packs already selected remove button doesn’t become active – incorrect |  | As per the security file admin does not have the permission to remove packs